## 0. Test setup
Do this BEFORE the walk-through: create test accounts, then add products
Email tip: Gmail ignores anything after a + sign, so rgbkart+shop1@gmail.com arrives in the rgbkart@gmail.com inbox, but RGBKart treats it as a separate account. You don't need new mailboxes.
A. Accounts to create
# | Account | Sign-up email (suggested) | How | Shop / name idea | Done? | Notes
A1 | Shop A (Gadgets, Dhaka) | rgbkart+shopa@gmail.com | login.html → Sign up → I want to sell; then Admin → Sellers → Approve | Test Gadget House · Dhaka · store pickup ON
A2 | Shop B (Fashion, Chattogram) | rgbkart+shopb@gmail.com | Same as A1 | Test Fashion Corner · Chattogram
A3 | Shop C (Home & grocery, Dhaka) | support@rgbkart.com | Same as A1 | Test Home Bazar · Dhaka
A4 | Customer 1 | kabiaritc@gmail.com | login.html → Sign up (customer) | Dhaka address
A5 | Customer 2 | rgbkart+cust2@gmail.com | Same as A4 | Outside Dhaka address (e.g. Sylhet)
A6 | Customer 3 | rgbkart+cust3@gmail.com | Same as A4 | Use it on your phone
A7 | One-time seller | (no account) | Private window → rgbkart.com/sell.html | Your name + a phone number
A8 | Admin | rgbkart@gmail.com | Already exists | Approves everything; adds products with options (only admin can)
B. Products to add (20) - each one tests different options
# | Who adds it | Example product | Price / stock | Options to set | What it tests | Done?
P1 | Shop A | Smartphone (brand new) | ৳18,000 · stock 10 | Then pay Featured 7 days (৳20) with a TrxID | Featured badge, Featured first in search, locked title/stock, payment check
P2 | Shop A | Wireless earbuds | ৳1,200 · stock 2 | Sale price ৳999 | Sale tag, 'only 2 left'
P3 | Shop A | USB-C cable | ৳250 · stock 100 | Bulk prices: 5+ = ৳220, 10+ = ৳200; Free delivery | Bulk price in cart, free delivery
P4 | Shop A | Used laptop | ৳35,000 · stock 1 | Condition: Used | Used label; first-order COD limit (over ৳20,000)
P5 | Shop A | Refrigerator | ৳45,000 · stock 3 | Parcel type: Heavy; ships to Inside Dhaka only | Heavy delivery methods, Dhaka-only area
P6 | Shop A | Power bank | ৳1,500 · stock 0 | Out of stock | Can't be added to cart
P7 | Shop A | Gaming console | ৳55,000 · stock 0 | Pre-order (ships later) | Pre-order label and note
P8 | Shop B | Cotton saree | ৳3,500 · stock 5 | Return policy 15 days; Bangla title + description | Return button, Bangla page
P9 | Shop B | Leather shoes | ৳2,200 · stock 8 | Return policy: No returns | No return button after delivery
P10 | Shop B | Glass flower vase | ৳800 · stock 6 | Parcel type: Fragile | Fragile delivery methods
P11 | Shop B | Perfume 100 ml | ৳1,500 · stock 10 | Parcel type: Flammable | Flammable delivery method
P12 | Shop B | Tailoring service | ৳600 | Type: Service | Service product shows correctly
P13 | Shop C | Miniket rice 25 kg | ৳1,800 · stock 40 | Parcel type: Heavy; bulk 3+ = ৳1,750 | Heavy + bulk together
P14 | Shop C | Soybean oil 5 L | ৳900 · stock 30 | Ships same day | Delivery time label
P15 | Shop C | Gift hamper | ৳2,500 · stock 4 | Then make coupon TEST10 (10%, min ৳500) in Coupons | Coupon in cart
P16 | One-time seller | Used bicycle | ৳8,000 | FREE listing; price negotiable | Phone hidden, message only, negotiable
P17 | One-time seller | Used motorbike | ৳95,000 | FEATURED listing (pay with TrxID); Parcel: Vehicle | Call/WhatsApp shown after payment, vehicle delivery
P18 | Admin (RGBKart Official) | T-shirt | ৳450 | Admin → Add product with options: Size S/M/L/XL × Colour Red/Green; XL +৳50 | Products with options (only admin can add)
P19 | Admin | Any approved product | - | Admin → Products → Make Featured (free) | Free Featured, ৳0 in reports
P20 | Admin | Any approved product | - | Admin → Products → % VAT 15 (VAT stays OFF until you switch it on) | VAT per product (test only if you plan to use VAT)
Tips
• | Add 1-3 photos to every product (phone photos are fine) so the pages look real.
• | After each shop adds products, approve them in Admin → Products (one with 'Reject' + a note, to test that too).
• | Each shop: Seller Center → Delivery, tick methods and set fees (Shop A: also 'Free delivery over ৳5,000').
• | Keep the browsers apart: admin in Chrome, shops in a private window or Edge, customers on the phone.
• | When the real launch comes, delete the test shops and customers in Admin → Users (one click each).

## Walk-through
RGBKart: live site walk-through (rgbkart.com)
Go top to bottom. In 'Result' choose Pass, Fail, Not sure or Skip. Write anything odd in Notes.
No. | Item | What to do | What you should see | Account / window | Result | Notes / what went wrong
1. First look: home page (no sign-in)
1.1 | Site opens | Open https://rgbkart.com on the computer | Home page loads with green header, basket logo, 'Red & Green Basket' wordmark and tagline | Guest (private window)
1.2 | www and old address | Open www.rgbkart.com and rgbkartdemo.hkmanik.com | Both end up on https://rgbkart.com (padlock shown) | Guest (private window)
1.3 | Categories grid | Look at the 6×2 category boxes; click one | Pictures/icons show; click opens that category's products | Guest (private window)
1.4 | Home sections | Scroll the whole home page | Sections with products show; empty sections are hidden, no broken boxes | Guest (private window)
1.5 | Top shops row | Watch the Top shops row; hover on it | Shop cards glide; stop while the mouse is on them | Guest (private window)
1.6 | Main menu | Open 'All categories' and each menu link | Panel opens; every link goes to a working page | Guest (private window)
1.7 | Footer | Click every footer link (About, Contact, Terms, Privacy, Returns, Seller rules) | Each page opens; note any [bracket] text still to be filled | Guest (private window)
1.8 | Wrong address | Open https://rgbkart.com/abc | Friendly 'page not found' page with a way back | Guest (private window)
2. Bangla / English
2.1 | Switch to Bangla | Click the language button in the menu bar | Menu, buttons, headings change to Bangla; Bangla font looks right | Guest (private window)
2.2 | Bangla everywhere | With Bangla on, open a category, a product, the cart | Category names, labels and prices (Bangla digits) are in Bangla; note any English left | Guest (private window)
2.3 | Remembered | Close the tab, open rgbkart.com again | Still in Bangla; switch back to English | Guest (private window)
3. Finding products
3.1 | Search words | Type a product word in the header search | Matching products; Featured first, then newest | Guest (private window)
3.2 | Search a shop / category | Search a shop name, then a category name | 'Shops' row and category buttons appear above products | Guest (private window)
3.3 | Search in Bangla | Search a Bangla word | Bangla titles/categories are found | Guest (private window)
3.4 | Filters and sort | On a category page use price, condition, rating filters and each sort | List changes correctly; page numbers work | Guest (private window)
3.5 | Nothing found | Search 'zzzz' | Polite 'nothing found' message | Guest (private window)
4. Product page and shop page
4.1 | Product page | Open any product | Photos, price, stock, description, delivery info, seller box | Guest (private window)
4.2 | Visit shop | Click 'Visit shop' | Shop page: banner, logo, contact, about, products, search and sort | Guest (private window)
4.3 | Share | Click Share on a product; paste the link in WhatsApp/Messenger | Preview shows picture, title and price | Guest (private window)
4.4 | Ask a question (guest) | Ask a question in the Questions box | 'Sent' message; seller gets it later (step 9) | Guest (private window)
4.5 | Report | Click 'Report' on a product, choose a reason | Thank-you message; Admin sees it (step 12) | Guest (private window)
4.6 | Free one-time listing contact | Open a FREE one-time seller listing (after step 7) | Phone NOT shown; only 'Message' on RGBKart | Guest (private window)
5. Customer account
5.1 | Sign up | login.html → Sign up as customer with kabiaritc@gmail.com | Confirmation email arrives from no-reply@rgbkart.com within a minute | Customer (kabiaritc@gmail.com)
5.2 | Confirm and sign in | Click the email link, then sign in | Lands on My account | Customer (kabiaritc@gmail.com)
5.3 | Profile and addresses | Edit name/phone; add 2 addresses; make one default | Saved; default marked | Customer (kabiaritc@gmail.com)
5.4 | Forgot password | Sign out → 'Forgot password' → follow the email | Reset email arrives; new password works | Customer (kabiaritc@gmail.com)
5.5 | Wishlist | Tap ♥ on 2 products, open Wishlist | Both listed; heart count in header | Customer (kabiaritc@gmail.com)
5.6 | Lists follow you | Sign in on the phone with the same account | Same wishlist and cart on the phone | Customer (kabiaritc@gmail.com)
6. Shop (seller) setup
6.1 | Seller sign-up | Private window: sign up as seller with support@rgbkart.com, fill shop details | 'Waiting for approval' message | Test shop (support@rgbkart.com)
6.2 | Approve the shop | Admin → Sellers → approve the new shop | Shop gets 'Shop approved' alert + email | Admin (rgbkart@gmail.com)
6.3 | Shop profile | Seller Center: logo, banner, about, phone, WhatsApp | Shows on store page | Test shop (support@rgbkart.com)
6.4 | Delivery | Seller Center → Delivery: tick methods, set fees, free delivery over | Saved; fees above admin maximum are refused | Test shop (support@rgbkart.com)
6.5 | Add products | Add 3 products: one simple, one with bulk prices, one Heavy parcel; with photos | Each says 'waiting for review' | Test shop (support@rgbkart.com)
6.6 | Coupon | Seller Center → Coupons: make TEST10 (10%, min ৳500) | Coupon listed | Test shop (support@rgbkart.com)
6.7 | Get verified | Seller Center → Get verified: upload an NID photo | 'Pending' status | Test shop (support@rgbkart.com)
7. One-time seller (no account)
7.1 | Free listing | Private window → sell.html → list one item FREE | Listing sent for review; phone hidden on the live listing | One-time seller (private window)
7.2 | Featured listing | List a second item and choose Featured | Shows fee and bKash/Nagad/Upay numbers; TrxID box | One-time seller (private window)
7.3 | Pay (test) | Send a small real payment or a test TrxID | 'Payment sent, waiting for check' | One-time seller (private window)
8. Admin review and payments
8.1 | Sign in as Master Admin | Sign in with rgbkart@gmail.com → My account → ⚙ Admin dashboard | Dashboard; status line shows 'Email alerts: … sent' | Admin (rgbkart@gmail.com)
8.2 | Approve products | Admin → Products: approve 2, reject 1 with a note | Seller gets alerts + emails | Admin (rgbkart@gmail.com)
8.3 | Verify payment | Admin → Payments: verify the TrxID from 7.3 | Listing becomes Featured; call/WhatsApp now visible on it | Admin (rgbkart@gmail.com)
8.4 | Featured lock | As the shop, try to edit the title/stock of a Featured product | Those boxes are locked | Test shop (support@rgbkart.com)
8.5 | Free Featured | Admin → Products: Make Featured (free) on one product | Featured badge; ৳0 in reports | Admin (rgbkart@gmail.com)
8.6 | Verify shop | Admin → Verification: approve the NID from 6.7 | '✓ Verified shop' on store and product pages | Admin (rgbkart@gmail.com)
8.7 | Advert | Seller Center → Advertise: book a 1-day ad; admin verifies payment | Ad shows in its place on the site | Test shop (support@rgbkart.com)
9. Buying (cash on delivery)
9.1 | Add to cart | As customer, add products from the test shop and one other shop | Cart grouped by shop with delivery choice each | Customer (kabiaritc@gmail.com)
9.2 | Bulk price | Raise quantity past the bulk price step | Lower unit price applied | Customer (kabiaritc@gmail.com)
9.3 | Coupon | Enter TEST10 in the shop's box (under and over ৳500) | Refused under minimum; discount shown above it | Customer (kabiaritc@gmail.com)
9.4 | Delivery rules | Check Inside / Outside Dhaka / Pickup; the Heavy item | Fees match the shop's; Heavy item only offers heavy methods | Customer (kabiaritc@gmail.com)
9.5 | COD limit | Put a very expensive cart (over ৳20,000 first order) | Limit note and Place order disabled | Customer (kabiaritc@gmail.com)
9.6 | Place order | Choose saved address, place a normal order | Order number(s), one per shop; stock goes down | Customer (kabiaritc@gmail.com)
9.7 | Emails | Check both inboxes within 5–10 min | Customer: order placed; Shop: new order | Customer (kabiaritc@gmail.com)
9.8 | Guest order | Private window, order without an account | Order placed with an anonymous sign-in | Guest (private window)
10. Shop handles the order
10.1 | See the order | Seller Center → Orders | New order card with buyer history (new / trusted / watch) | Test shop (support@rgbkart.com)
10.2 | Move it along | Confirm → Packed → Shipped → Delivered | Customer sees each step on My orders and gets an alert each time | Test shop (support@rgbkart.com)
10.3 | Print | Print invoice, packing list and label; try Printer setup | Correct paper size, logo, barcode, discount and VAT lines | Test shop (support@rgbkart.com)
10.4 | Messages | Customer messages the shop from the order; shop replies | Both see the chat on Messages page; badge in header | Customer (kabiaritc@gmail.com)
10.5 | Answer question | Seller Center → Questions: answer the one from 4.4 | Answer shows on the product page | Test shop (support@rgbkart.com)
11. After the order
11.1 | Cancel (early) | Customer places another order and cancels it at once with a reason | Cancelled; stock returns; shop alerted | Customer (kabiaritc@gmail.com)
11.2 | Ask to cancel (late) | After the shop marks Packed, customer 'Ask the shop to cancel' | Shop sees yellow box; Accept / Decline works | Customer (kabiaritc@gmail.com)
11.3 | Review | On the delivered order: Rate this order (product + shop) | Stars on product, card and shop; shop gets alert | Customer (kabiaritc@gmail.com)
11.4 | Seller reply | Seller Center → Reviews: reply | Customer gets 'The shop replied' | Test shop (support@rgbkart.com)
11.5 | Return | On the delivered item: Return this item, add a photo | Shop → Returns: approve → received; stock back | Customer (kabiaritc@gmail.com)
11.6 | Report a seller | Customer reports the shop from the order | Admin → Complaints shows it | Customer (kabiaritc@gmail.com)
12. Admin tools
12.1 | Home page sections | Admin → Home page: rename, reorder, hide a section | Home page changes | Admin (rgbkart@gmail.com)
12.2 | Main menu | Admin → Main menu: add and remove a link | Menu updates | Admin (rgbkart@gmail.com)
12.3 | Categories | Admin → Categories: upload a picture, check Bangla name | Picture shows on home | Admin (rgbkart@gmail.com)
12.4 | Featured & ad rates | Check 7/15/30 days ৳20/35/50 and ad rates | Prices right; sellers see the same | Admin (rgbkart@gmail.com)
12.5 | Payment numbers | Admin → Payments: check bKash/Nagad/Upay numbers | Your real numbers | Admin (rgbkart@gmail.com)
12.6 | Orders settings | Admin → Orders: COD limits, Cancellation rules, VAT (keep off), Delivery methods | Values as you want them | Admin (rgbkart@gmail.com)
12.7 | Complaints & Q&A | Admin → Complaints, Questions, Reviews, Returns | Items from steps 4, 10, 11 listed; hide/close works | Admin (rgbkart@gmail.com)
12.8 | Users | Admin → Users: filters; block then unblock the test customer | Blocked person can't sign in; unblock restores | Admin (rgbkart@gmail.com)
12.9 | Team | Admin → Team: check hkmanik@gmail.com is Co-admin | Correct roles | Admin (rgbkart@gmail.com)
12.10 | Activity log | Admin → Activity log | Your admin actions from today listed | Admin (rgbkart@gmail.com)
12.11 | Reports | Admin → Reports: this month; Download Excel | File opens in Excel with Summary, Orders, Payments, Top shops/products | Admin (rgbkart@gmail.com)
12.12 | Pages & policies | Admin → Pages & policies: fill [brackets], add Bangla | Footer pages updated | Admin (rgbkart@gmail.com)
13. Phone and other checks
13.1 | Phone look | Repeat a few steps (home, product, cart, checkout) on a phone | Nothing cut off; menu and buttons easy to tap | Customer (kabiaritc@gmail.com)
13.2 | Add to home screen | Phone browser → Add to Home screen | RGBKart icon | Customer (kabiaritc@gmail.com)
13.3 | Alerts page and bell | Open Alerts; switch email alerts off and on | Bell shows unread count; switch saves | Customer (kabiaritc@gmail.com)
13.4 | Google | Search 'rgbkart' on Google after a few days | Site appears (can take 1–2 weeks) | Guest (private window)
13.5 | Speed | Note any page that feels slow | Most pages open in 2–3 seconds | Guest (private window)
14. Clean up after testing
14.1 | Test orders | Admin → Users: delete the test customer and the guest (or keep for demos) | Their orders disappear | Admin (rgbkart@gmail.com)
14.2 | Test shop | Delete or keep the support@rgbkart.com shop | As you decide | Admin (rgbkart@gmail.com)
14.3 | Send me the list | Send me this file with Fail / Not sure rows and notes | I fix them one by one | Admin (rgbkart@gmail.com)

## Summary
Progress
Status | Count
Pass | 0
Fail | 0
Not sure | 0
Skip | 0
Not checked yet | 84
Total checks | 84